## Sheet1
| Codes | Activity | Description | Predecessors | Successors | Early start | Early finish | Late start | Late finish | Critical
0 | Gate | Start |  | [] | ['A', 'B'] | 0 | 0 | 0 | 0 | YES
1 | Task | A | Agreement of the owner | ['Start'] | ['C', 'D', 'E'] | 0 | 4 | -1.4739 | 3.0094 | YES
2 | Task | B | Preparation of the ground | ['Start'] | ['D'] | 0 | 2 | 4.2206 | 6.8282 | NO
3 | Task | C | Order of materials | ['A'] | ['F'] | 4 | 5 | 4.3546 | 5.3546 | NO
4 | Task | D | Excavation | ['A', 'B'] | ['G'] | 4 | 5 | 6.8282 | 7.8282 | NO
5 | Task | E | Order of doors and windows | ['A'] | ['H'] | 4 | 6 | 3.0094 | 5.3776 | YES
6 | Task | F | Delivery of materials | ['C'] | ['G'] | 5 | 7 | 5.3546 | 7.8282 | NO
7 | Task | G | Concrete foundations | ['D', 'F'] | ['J'] | 7 | 9 | 7.8282 | 10.4653 | NO
8 | Task | H | Delivery of doors and windows | ['E'] | ['K'] | 6 | 15 | 5.3776 | 15 | YES
9 | Task | J | Frame, roofs, walls | ['G'] | ['K'] | 9 | 13 | 10.4653 | 15 | NO
10 | Task | K | Installation of doors and windows | ['H', 'J'] | ['End'] | 15 | 16 | 15 | 16 | YES
11 | Gate | End |  | ['K'] | [] | 16 | 16 | 16 | 16 | YES